## Slide 1: Tool: AI Roadmap for HR
Gartner for HR Leaders
Notes: Ver 2026-0114
Presenter's Name
Presenter's Name

## Slide 2: How to Use This Tool
In the next slide, we present six AI workstreams with their top-level tasks.
1
Click on each workstream to see a typical roadmap. You can also click for a detailed description and resources found in the appendix.
2
At any point, you can click the “back” icon to return to the main screen.
3
Go full screen for the best experience!

## Slide 3: AI Roadmap for the HR Function at a Glance
Source and prioritize AI use cases
Measure value and realize benefits
Develop the AI business case and manage funding
Define and align the AI roadmap for HR
Standardize practices and share lessons on AI value realization
Manage AI portfolio and interdependencies
Continuously identify and optimize the portfolio, and lead innovation
AI data and systems for the HR function
Initial activities
Advanced activities
AI strategy for the HR function
Analyze AI trends and impact on HR
Measure HR function
readiness for AI
Set AI vision and ambition
Continually evolve the AI strategy
Develop and align the AI strategy document
AI value for the HR function
AI impact on work in the HR function
Promote new AI use cases in HR workflows
Redesign HR jobs and teams for new AI-enabled value streams
Define the role of human and AI in HR value streams
Augment existing ways of working with AI
Preserve human interactions
for high-impact moments
Plan and document workflows for human effort and dependency
Adopt a dynamic work redesign to capture emerging value
Transform the HR operating model by deploying the latest AI solutions
Develop new HR products/ services beyond the boundaries of the HR function
Conduct an HR workforce sentiment and readiness assessment, and assess the impact of AI on HR
Integrate AI literacy into broader L&D programs
Foster knowledge-sharing and best practice communities
Implement AI literacy training and upskilling, and measure effectiveness
Foster an innovation culture
Design targeted interventions to
future-proof the workforce for AI
Recognize and reward AI-driven innovation
AI people and culture for the HR function
AI governance
for the HR function
Form an HR AI governance team
Implement legal and regulatory frameworks and policies for HR
Customize enterprise AI ethics, risk, security and safety for HR
Participate in the enterprise AI governance council
Communicate and train HR staff on AI governance mandate within HR
Define governance decision rights and stakeholders in HR
Ensure AI governance adherence for HR and third-party vendors
Handle exceptions and escalations
Create employee and candidate AI transparency
Design AI solutions as part of the HR technology strategy
Configure AI with extensibility and platform controls
Manage AI features in the HR technology portfolio
Maintain HR AI data quality, integrity and behavior
Develop and provide metadata
Define AI's role at the system level
Acquire, prepare, standardize and integrate HR data for AI
Define AI architecture, integration and controls
Measure effectiveness of data in HR AI use cases
Assure security and privacy for HR data
Separate workflows from tools
Provide AI data provenance and traceability
Create an AI runtime and execution environment
Develop and enforce HR data governance controls, policies and processes

## Slide 4: AI Strategy for the HR Function Illustrative Roadmap
AI strategy for the HR function
Continually evolve the AI strategy
Analyze current AI trends and impact on HR
Set AI vision and ambition
Measure HR function
readiness for AI
Develop and align AI strategy document
See Appendix for detailed descriptions (click here)
Initial activities
Advanced activities

## Slide 5: AI Value for the HR Function Roadmap Activities
See Appendix for detailed descriptions (click here)
AI value for the HR function
Initial activities
Advanced activities
Source and prioritize
AI use cases
Continuously identify and optimize the portfolio, and lead innovation
Develop the AI business case
and manage funding
Measure value and realize benefits
Standardize practices and share lessons on AI value realization
Manage AI portfolio and interdependencies
Define and align the
AI roadmap for HR

## Slide 6: AI Impact on Work in the HR Function Roadmap Activities
See Appendix for detailed descriptions (click here)
AI impact on work in the HR function
Develop new HR products/services beyond the boundaries of the HR function
Redesign HR jobs and teams for new AI-enabled value streams
Adopt a dynamic work redesign to capture emerging value
Transform the HR operating model by deploying the latest AI solutions
Initial activities
Advanced activities
Plan and document workflows for human effort and dependency
Preserve human interactions for high-impact moments
Augment existing ways of working with AI
Promote new AI use cases
in HR workflows
Define the role of humans and AI in HR value streams

## Slide 7: AI People and Culture for the HR Function Roadmap Activities
Initial activities
Advanced activities
See Appendix for detailed descriptions (click here)
AI people and culture for the HR function
Integrate AI literacy into broader L&D programs
Design targeted interventions to future-proof the workforce for AI
Conduct an HR workforce sentiment and readiness assessment, and assess the impact of AI on HR
Foster an innovation culture
Recognize and reward
AI-driven innovation
Foster knowledge-sharing and best practice communities
Implement AI literacy training and upskilling, and measure effectiveness

## Slide 8: AI Governance for the HR Function Roadmap Activities
Initial activities
Advanced activities
See Appendix for detailed descriptions (click here)
AI governance for the HR function
Handle exceptions and escalations
Communicate and train HR staff on AI governance mandate within HR
Define governance decision rights and stakeholders in HR
Implement legal and regulatory frameworks and policies for HR
Customize enterprise AI ethics, risk, security, and safety for HR
Participate in the enterprise AI governance council
Create employee and candidate transparency
Form an HR AI governance team
Ensure AI governance adherence for HR and third-party vendors

## Slide 9: AI Data and Systems for the HR Function Roadmap Activities
Initial activities
Advanced activities
See Appendix for detailed descriptions (click here)
AI data and systems for the HR function
Define AI’s role at the system level
Configure AI with extensibility and platform controls
Develop and enforce HR data governance controls, policies and processes
Provide AI data provenance and traceability
Develop and provide metadata
Assure security and privacy for HR data
Maintain HR AI data quality, integrity, and behavior
Measure effectiveness of data in HR AI use cases
Separate workflows from tools
Define AI architecture, integrations, and controls
Manage AI features in technology portfolio
Create an AI runtime and execution environment
Acquire, prepare, standardize and integrate HR data for AI
Design AI solutions as part of HR technology strategy

## Slide 10: Appendix: Detailed Task Descriptions

## Slide 11: AI Strategy for HR Function: Detailed Activities
Activity | Steps | Supporting resources
Analyze current AI trends and impact on HR | Assess AI trends and key developments to determine how they will impact HR’s ability to deliver services and organizational value. Perform a strategic gap analysis to compare your HR function's current AI capabilities against those of your competitors. Prioritize identified AI trends and categorize initiatives based on their strategic intent and differentiated impact across various HR processes. Identify where AI can generate the greatest business value across the HR function. Summarize the key trends and their potential impact in a short report. | Top Insights on AI for CHROs, Hype Cycle for AI in Human Resources, 2025, The Impact of AI on the HR Operating Model, Tool: AI Impact-Value Navigator for HR Processes
Set AI vision and ambition | Understand your organization’s goals, HR strategy and prioritized outcomes to tailor an appropriate vision. Identify and formulate an AI vision that answers the question about the importance of AI to the HR function, given the above context. Ensure that the vision is actionable and relatable across every role within your function. Validate and calibrate this vision statement in a discussion with senior leadership. Leverage the vision to define guiding principles that at a minimum address goals, value, risks, adoption and alignment. | Tool: Develop an HR-Focused AI Strategy (Vision Section)
Measure HR function readiness for AI | Utilize Gartner’s framework to measure the HR function’s AI maturity. Run a baseline assessment to identify gaps between current and target state. If possible, benchmark this against similar organizations. Gather feedback from a diverse set of stakeholders around the current state of AI within the function. Identify priority capability gaps for being able to achieve the AI vision (this will inform the rest of the roadmap). | AI Maturity Assessment for the HR Function
Develop and align the AI strategy document | Engaging with HRLT and other relevant stakeholders (e.g., IT) collect and review the organization’s overall AI strategy and long-term ambition. Collaborate with HR, IT and AI teams to align on shared goals, clarify roles and ensure buy-in. Formulate a risk assessment and adoption plan for the implementation of AI in the HR function while outlining a high-level investment approach (deciding whether to leverage existing technology, buy, or build). Develop a comprehensive presentation for executive approval and to gain funding. Ensure alignment is bi-directional as changes in business strategy and AI trends shift. | Tool: Develop an HR-Focused AI Strategy
Continually evolve the AI strategy | Set up a process that triggers a revision to the HR-AI strategy when HR/technology/industry trends change significantly or the business strategy shifts. This can include a periodic annual refresh independent of changes. Define a plan to refresh, including the analysis required (e.g., external trend analysis, maturity assessment), stakeholders to be involved and the key activities to update the strategy. | Tool: Develop an HR-Focused AI Strategy

## Slide 12: AI Value for HR Function: Detailed Activities
Activity | Steps | Supporting resources
Source and prioritize AI use cases | Gather AI ideas via HR forums, leader interviews, employee inputs, and vendor demos. Document user needs, data sources, process pain points, and constraints. Use an intake form; review with IT, and business stakeholders. Score value, risk, feasibility, effort, complexity, and time-to-impact with IT and legal input. Revisit and adjust scoring in quarterly business reviews. | AI Use Case Insights
Define and align the AI roadmap for HR | Set quick wins and long-term goals as an HR leadership team. Map skills, processes, and tech gaps, and governance needs in collaboration with IT. Build a phased roadmap; validate with PMO and business. Present roadmap to IT, finance, and business sponsors. Identify cross-team dependencies in workshops. Gain sign-off on priorities, roles, and timelines. | Toolkit: Measure and Communicate the ROI of AI in HR
Develop the AI business case and manage funding | Quantify costs, benefits and risks in collaboration with finance and procurement. Define adoption plans and funding needs for each project. Track spend and ROI; adjust with finance and project leads. | Toolkit: Measure and Communicate the ROI of AI in HR
Manage AI portfolio and interdependencies | Review project status, resource needs, and dependencies in monthly PMO meetings. Align integration plans and release plans with IT architects and vendors. Govern with a cross-functional steering committee. | Design an AI Portfolio to Achieve Valued Outcomes
Measure value and realize benefits | Define metrics with IT and business stakeholders. Monitor KPIs on high-priority use cases (e.g., hiring, retention, and productivity) monthly. Review outcomes postlaunch; actively manage benefits and adjust as needed. | Toolkit: Measure and Communicate the ROI of AI in HR
Standardize practices and share lessons on AI value realization | Create guides and templates on AI use with IT. Build reusable docs and prompt libraries for teams. Share insights on best practices in HR all-hands and exec briefings. | Toolkit: Measure and Communicate the ROI of AI in HR
Continuously identify and optimize the portfolio, and lead innovation | Hold quarterly reviews to reprioritize or sunset projects. Use dashboards to track adoption and value delivery. Run innovation labs to test and scale new AI ideas, positioning HR as an innovation leader. | Toolkit: Measure and Communicate the ROI of AI in HR

## Slide 13: AI Impact on Work for HR Function: Detailed Activities (1 of 2)
Activity | Steps | Supporting resources
Promote new AI use cases in HR workflows | Identify “likely-win” AI use cases that are feasible, with high potential value. Communicate prioritized use cases and set expectations that HR teams should experiment. Design an inclusive AI skills training based on different levels of employee AI maturity. Set expectations of how much time employee should spend experimenting. Share success stories to promote more widespread adoption. | Tool: Prioritize HR Processes for AI Transformation, Case Study: Building an AI-Ready Enterprise Workforce
Augment existing ways of working with AI | Stand up an HR work redesign team. Build communications and language that describe AI as a tool, not a teammate, to create an abundance mindset (not a scarcity minded). Design and lead team-based AI experimentation built around solving for work friction in existing processes. Give teams explicit guidance on how they should use freed up time. | Case Study: Enable Effective AI Use Through Work-Based Learning, Case Study: AI Time Save and Use Framework to Drive Growth
Define the role of human and AI in HR value streams | Define the products HR deliver the enterprise based on outcomes they deliver (it is critical you don’t default to mapping HR’s core processes). Lead value stream mapping workshops for each product; map the key steps taken from start to value creation, focusing on what work is done rather than who does the work. For each step in the value stream list the key tasks, key skills to deliver, owners and key interdependencies. Score each tasks as best suited for human only, humans augmented by AI, or AI only. | Playbook: Redesigning HR Processes for AI, How to Redesign Processes and Workflows to Drive Organizational Strategy, Redesign Work to Achieve AI Value
Plan and document workflows for human effort and dependency | Agree together with your process owners (including key stakeholders such as HR team members, customers, data owners) on the HR processes in scope of the documenting. Map the workflow in scope to develop a thorough understanding of its key components (e.g., process steps for HR roles and customers involved as well as key customer touchpoints and human dependency). Use your mapped process to investigate the inefficiencies and quality and to collect feedback from customers who are affected by the process on key pain points while interacting with HR across key moments. Analyze both HR’s and customers’ expectations and preferences to clearly articulate which process-specific challenges need to be solved and how the ideal experience of the selected HR processes would look including human effort and dependency. | Tool: HR Process Redesign Methodology
Preserve human interactions for high-impact moments | Create criteria for when a human interaction is critical in HR’s products and services. Assess all HR value streams to identify moments that matter when a human interaction will be critical. Set guardrails to protect identified human interaction moments. Plan for ripple effect new human interactions that arise from AI being embedded in products and workflows. | What Kind of Work Still Matters in the Age of AI?, AI’s Ripple Effect on Jobs and Organizations

## Slide 14: AI Impact on Work for HR Function: Detailed Activities (2 of 2)
Activity | Steps | Supporting resources
Redesign specific HR jobs and teams for new AI-enabled value streams | Stand up temporary fusion teams accountable for creating new human-AI value streams. They will follow product management ways of working. Formalize fusion teams into standing teams (which will be your new COEs) once new human-AI value streams are sufficiently established. Map the key tasks of HR jobs, and track which tasks remain with humans, are delivered jointly buy humans and AI, and move to being done by AI. Update job expectations for HR roles once the tasks have change sufficiently. Map skills changes for updated jobs: track enduring skills, skills that will atrophy and emerging skills. Identify the skills atrophying that will be risky moving forward. | Case Study: Redesign Work Processes to Unlock GenAI Transformation, Case Study: Human-Centric AI Talent Roadmap (Red Hat)
Adopt dynamic work redesign to capture emerging value | Assign accountability for ongoing evaluation to a standing team, with a defined cadence of review (e.g., quarterly). Set triggers for prompting reviews of processes, jobs and team structures to replace the set review cadence (example triggers: notable upgrades in AI technology at your enterprise; promising experimentation within the function; changes to HR’s products; rise in work friction). Standardize your function’s trigger evaluation process for enacting changes to processes, jobs and/or team structures. Standardize your function’s playbook for updating processes, jobs and/or team structures in response to a valid trigger. | Redesign Work to Achieve AI Value, Case Study: Continuous Improvement Process for Digital HR Transformation
Transform the HR operating model by deploying latest AI solutions | Create a HR Innovation Command Center team responsible for the function’s innovations. Build/buy your HR staff’s aggregate data & digital savviness so the function can deliver new digital HR products more quickly. Restructure HR’s CoE teams as fusion teams focused on delivering high-quality value streams/products. | The Impact of AI on the HR Operating Model
Develop new HR products/services beyond the boundaries of the HR function | Establish core HR products as platform services that different parts of the business can avail of and personalize. Embed core HR digital products within broader employee interfaces comprising services from all corporate functions. Create HR “patches” that can be embedded within AI tools being built across the enterprise. Run innovation labs to test and scale new AI based HR products and services while stopping solutions not driving value to the enterprise. | A CIO’s Guide to Platform Teams and Roles, HR’s Future Operating Model: What Capabilities Will Differentiate HR in an AI Era?

## Slide 15: AI People and Culture for HR Function: Detailed Activities (1 of 2)
Activity | Steps | Supporting resources
Implement AI literacy training and upskilling, and measure effectiveness | Use diagnostic assessments to identify baseline AI literacy and specific skill gaps across HR roles and levels. Align training content with business priorities, such as ethical AI use, data privacy, and HR-specific applications. Foster a 70/20/10 learning culture and continuous development through blended learning (e-learning, workshops, role-based training, microlearnings, peer coaching and access to AI learning communities) to accommodate diverse learning styles and maximize engagement. Define success metrics by establishing KPIs such as knowledge retention, behavioral change, and business impact (e.g., process automation), measuring gains via practical exercises, quizzes, and monitoring of AI tool adoption. Collect qualitative insights via surveys and focus groups, then share results with stakeholders to identify improvement areas and refine future delivery. | How HR Can Build AI Literacy to Realize ROI, How to Measure the Effectiveness of AI Learning Programs
Integrate AI literacy into broader L&D programs | Audit existing L&D offerings to identify opportunities to embed AI literacy modules into onboarding, leadership development, and functional HR training. Collaborate with L&D and business leaders to ensure AI literacy aligns with the organizational strategy and is relevant to HR’s evolving role. Ensure that AI literacy is taught as part of ongoing HR development, so every HR staff member encounters AI topics regularly, not just in a separate course. Communicate the importance of AI literacy for HR’s future-readiness and encourage participation. Regularly evaluate and refresh AI-related content in L&D programs to keep pace with new technologies and HR needs. | Essential HR Skills for Success in the AI Era
Conduct an HR workforce sentiment and readiness assessment, and assess the impact of AI on HR | Develop and deploy pulse surveys, interviews, or focus groups to regularly capture employee sentiment, readiness, and concerns regarding AI initiatives, utilizing real-time feedback loops during AI rollouts to identify emerging barriers. Segment results by role, team, and location to uncover trends and tailor communications or interventions for specific groups. Share findings transparently with leadership and employees to build trust and demonstrate responsiveness and foster a culture of trust regarding AI initiatives. Identify current and future HR role requirements to detect byproducts of AI (e.g., skills atrophy), while conducting workshops to understand qualitative shifts in job satisfaction, skill requirements, and workflow. Conduct interviews and workshops with impacted employees to understand track redeployment and upskilling outcomes to assess the effectiveness of support programs. | How We Talk About AI at Work Matters, Prepare for AI’s Unexpected Workforce Behavioral Byproducts, Case Study: Workforce Planning for Generative AI in Midsize Enterprises

## Slide 16: AI People and Culture for HR Function: Detailed Activities (2 of 2)
Activity | Steps | Supporting resources
Design targeted interventions to future-proof the workforce for AI | Develop role-based enablement journeys, customizing learning paths and interventions for different HR segments and roles. Provide just-in-time resources (such as toolkits, microlearning modules, and FAQs) to support employees as they encounter new AI-related tasks or challenges. Equip managers with enablement guides and talking points so they can support their teams effectively through AI-driven changes. Launch interventions and collect ongoing feedback from both employees and managers, using this input to refine support in real time. | Four Key Elements of a Talent Strategy That Drive Performance Today and Tomorrow
Foster knowledge-sharing and best practice communities | Identify and empower enablement champions or peer leaders within HR to drive knowledge-sharing and adoption of AI practices. Establish digital platforms or communities for sharing resources, success stories, and lessons learned. Encourage champions to lead local or virtual enablement sessions, fostering peer-to-peer learning and collaboration. Continuously update shared resources and best practices based on community feedback and evolving AI initiatives. | Case Study: Enable Effective AI Use Through Work-Based Learning
Foster a culture of innovation | Evaluate the current HR culture to understand existing behaviors and articulate a clear vision for an innovation-driven culture. Connect innovation initiatives to HR and business objectives, ensuring every employee understands their role in fostering innovation. Implement “culture hacks” such as designating time for innovation, encouraging idea sharing in meetings, and involving staff in creating new behaviors through collaboration, competitions, or gamification. Launch innovation challenges, cross-functional projects, and regular team-based exercises to encourage experimentation, proactive problem solving, and risk taking. | 2026 CHRO Priority: Strengthen Culture to Power Performance
Recognize and reward AI-driven innovation | Embed recognition moments into innovation challenges, team meetings, and cross-functional projects — celebrating not just successes but also creative risk taking and lessons learned. Establish formal recognition programs — such as awards, showcases, or organization-sponsored product pilot opportunities — for individuals and teams who demonstrate AI-driven innovation. Promote a culture where both peers and leaders can nominate colleagues for their innovative contributions, ensuring recognition is inclusive and visible across HR. Regularly communicate achievements and lessons learned from AI innovation through internal channels, reinforcing the innovation culture and inspiring others to participate. | Innovation Insight: Unlocking Engagement Through Recognition & Reward Solutions

## Slide 17: AI Governance for HR Function: Detailed Activities (1 of 3)
Activity | Steps | Supporting resources
Form an HR AI governance team | Clarify the purpose, mandate and scope of the HR AI governance team. Select members from key functional HR domains (e.g., HR technology, HR operations, talent COE, etc.). Define clear roles and responsibilities and establish ownership. Set team meeting structure, cadence, escalation paths, and decision-making workflows. Align with enterprise AI governance structures to ensure consistency. | Quick Answer: Do Enterprises Need an AI Board?
Participate in the enterprise AI governance council | Nominate and assign HR team members with decision authority and strong business understanding. Define HR governance input areas and clarify where HR contributes (e.g., workforce impact, employee data usage, ethical considerations, etc.). Establish structured reporting mechanisms from HR towards the enterprise AI governance council an HR AI use cases, risks or policy implications. Continuously feedback HR specific risks, insights and emerging HR-related AI challenges. Ensure enterprise decisions are translated and reported back into the HR AI governance team to ensure enterprise decisions are adapted into frameworks, policies and controls for HR. | Quick Answer: Do Enterprises Need an AI Board?
Define governance decision rights and stakeholders in HR | Identify key HR AI decisions and decision types (e.g., use case approval, vendor selection, risk classification). Define decision rights and authority levels for the HR AI governance team vs enterprise-AI governance team. Create governance workflows and escalation paths to define how decisions are made, reviewed, and escalated in high-risk cases. Implement clear documentation standards to ensure accountability and auditability. | Artificial Intelligence Requires an Extended Governance Framework, How to Design an Effective AI Governance Operating Model, Create an AI Literacy Roadmap to Drive Responsible and Productive AI

## Slide 18: AI Governance for HR Function: Detailed Activities (2 of 3)
Activity | Steps | Supporting resources
Customize enterprise AI ethics, risks, security and safety for HR | Identify HR-specific ethical risk areas (e.g., bias in talent decisions, explainability of AI-driven recommendations etc.), AI risk areas (e.g., employee data privacy concerns), and AI security and safety areas (e.g., access to sensitive employee data). Translate high-level enterprise AI ethical risks, AI risks, and AI security and safety principles for each HR use case, respectively. Define HR specific: – AI ethics frameworks, policies and controls and develop clear guidance on evaluating acceptable vs. nonacceptable AI use cases in HR processes and integrate ethical reviews into AI in HR use case approval. – AI risk frameworks, policies and controls and develop clear guidance on evaluating low vs. high-risk AI use cases in HR processes and develop mitigation measures (e.g., human-in-the-loop, bias testing, or data minimization). – AI security and safety frameworks, policies and controls and ensure strict governance sensitive employee data access. Ensure secure deployment of AI tools in HR environments and align with IT on infrastructure, vendor security, and system interfaces. Enable awareness and training on responsible AI in HR while implementing risk monitoring and security monitoring to detect misuse risks, unauthorized access detection, data leakages, and/or unintended model behavior. | Tool: Generative AI Policy Kit, Case Study: An AI Governance Framework for Managing Use Case Ethics, Tool: Identify and Mitigate Top GenAI Usage Risks
Implement legal and regulatory frameworks and policies for HR | Collaborate with the enterprise AI governance council to identify relevant legal and regulatory AI regulations impacting HR AI use. Define how legal and regulatory AI regulations impact HR activities (e.g., automated decision making in hiring) and translate requirements into HR process guidelines. Integrate legal and regulatory reviews into HR use case design, vendor selection, and deployment. Define documentation and audit requirements to ensure traceability of AI decisions and compliance with legal and regulatory AI regulations. Align with legal, compliance, and works councils to ensure stakeholder alignment, especially in regulated or employee-sensitive contexts. | 
Communicate and train HR staff on AI governance mandate within HR | Develop and deliver presentations for HR leaders on the importance of AI governance, highlighting HR-specific risks, key regulations, and the strategic benefits for HR processes. Identify different employee personas (e.g., executives, managers, front-line staff) to determine their specific education needs and create a general awareness program regarding AI risks. Create detailed training for specific segments including hands-on workshops, case studies, and Q&A sessions to clarify the governance mandate and gather feedback on AI-related concerns. Create and share simple materials (FAQs, infographics, guides) explaining the AI governance mandate, its HR relevance, and impact on daily HR work. Hold regular briefings with HR managers to share updates and success stories, while maintaining an ongoing process to keep stakeholders informed of AI advancements and regulatory changes. | Board Briefing: AI Regulatory Updates, Create an AI Literacy Roadmap to Drive Responsible and Productive AI

## Slide 19: AI Governance for HR Function: Detailed Activities (3 of 3)
Activity | Steps | Supporting resources
Create employee and candidate AI transparency | Communicate clear, accessible guidelines on how AI is used in HR, outlining what data is collected, how it’s processed, and the decisions AI supports. Inform employees and candidates of their rights related to AI in HR, including data access, correction, objection, and appeal mechanisms for AI-driven decisions. Ensure transparent consent by notifying employees and candidates when their data will be used in AI systems, specifying purpose and scope before collection or processing. Maintain dedicated channels for employees and candidates to ask questions or raise concerns about AI in HR, ensuring timely, clear responses. | Top HRBP Actions to Address the AI Fears of Employees
Ensure AI governance adherence for HR and third-party vendors | Establish a formal process to monitor, document, and address deviations from governance policies, including clear escalation paths for issues that cannot be immediately resolved. Continuously monitor HR AI systems using automated tools and manual checks to identify bias, fairness issues, and data quality concerns, allowing for the prompt mitigation of risks as they arise. Perform scheduled, in-depth reviews of AI outputs and HR process outcomes to evaluate long-term adherence to governance standards and capture lessons learned for future improvement. Translate enterprise security principles into HR-specific controls, ensuring strict governance over sensitive employee data access and identifying safety areas unique to the HR function. Align with IT to ensure the secure deployment of AI tools — focusing on vendor security and system interfaces — while implementing ongoing monitoring to detect unauthorized access, data leakage, or unintended model behavior. | Tool: Generative AI Policy Kit
Handle exceptions and escalations | Establish clear procedures for identifying and documenting exceptions in HR AI systems and processes that deviate from enterprise governance requirements. Assign responsibility for initial assessment and resolution of exceptions, ensuring prompt corrective actions and mitigation of compliance risks. Define escalation pathways for unresolved or high-impact exceptions, including criteria for when issues must be elevated to senior HR leadership or enterprise governance teams. Maintain records of exception handling and escalation outcomes, enabling ongoing review and continuous improvement of HR AI governance processes. | 

## Slide 20: AI Data and Systems for HR Function: Detailed Activities (1 of 4)
Activity | Steps | Supporting resources
Acquire, prepare, standardize and integrate HR data for AI | Identify specific HR AI use cases and define their unique data requirements to determine exactly what information is needed across the HR systems landscape. Obtain formal approvals from legal and data privacy teams before accessing employee data and document data ownership by recording origins and maintenance responsibilities. Clean HR data to remove errors and duplicates, anonymizing sensitive information where appropriate and organizing it into structured formats with clear labels for AI processing. Establish consistent data formats and naming conventions to ensure compatibility, then use ETL processes or APIs to automate and validate the merging of data from disparate HR systems. Convert raw data into a clean, numerical format that AI can effectively use for learning and predictions, then train and validate the solution to enhance accuracy and reliability. | 3 Steps to Establish AI-Ready HR Data How HR Tech Leaders Can Make HR Data AI-Ready, A Journey Guide to Deliver AI Success Through AI-Ready Data, Tool: AI Data Readiness Scorecard for HR, How to Assess and Improve Your Data Integration Maturity, Strengthen Data Integration Foundations for AI Success
Develop and provide metadata | Define metadata standards and structure by establishing clear definitions, formats, and standards for each data element, such as data type, allowed values, and update frequency. Implement data privacy and compliance measures by ensuring that metadata captures information on data sensitivity, access controls, and other compliance requirements. Develop a centralized, accessible metadata repository (e.g., data catalog or dictionary) where stakeholders and AI systems can retrieve HR metadata. | How HR Tech Leaders Can Make HR Data AI-Ready State of Metadata, Management: Aggressively Pursue Metadata to Enable AI and Generative AI
Provide AI data provenance and traceability | Record data sources, collection methods, dates, and key metadata, including origin, format, and preprocessing requirements. Store datasets securely with version control, tracking all changes and access logs for traceability. Log all data processing steps, noting who did what, when, and with which tools. Keep records of AI model training, including dataset versions, parameters, results, and provenance. Monitor and audit all data and model access or changes to ensure compliance and traceability | What Makes Data Management Leaders and Teams Successful Quick Answer: How Does Data Lineage Accelerate Data Management Capabilities?
Develop and enforce HR data governance controls, policies and processes | Identify gaps with HR data management and ensure compliance with regulations. Establish a data governance framework with clear roles, responsibilities, and ownership. Create and document HR data policies for access, security, privacy, retention, and quality, with controls for compliance. Implement processes and technology for data collection, storage, sharing, and reporting, supporting policy enforcement and audit trails. Train staff on governance, regularly audit, and refine controls to adapt to regulatory or business changes | Tool: Effective Data and Analytics Governance Playbook A Practical Guide to Data Governance for AI-Ready Data

## Slide 21: AI Data and Systems for HR Function: Detailed Activities (2 of 4)
Activity | Steps | Supporting resources
Assure security and privacy for HR data | Restrict HR data access to authorized users with role-based permissions and strong authentication. Encrypt HR data at rest and in transit to prevent unauthorized access. Regularly audit HR systems and assess vulnerabilities to address security risks. Enforce clear data handling policies for collection, storage, sharing, and disposal to ensure privacy compliance. Train HR staff on data security, privacy best practices, and recognizing threats | Practical Privacy — Managing HR Data
Maintain HR AI data quality, integrity and behavior | Establish data validation processes to ensure accuracy and completeness at the point of entry, while applying robust security measures like encryption and access controls to protect sensitive HR information. Monitor and audit datasets on a regular cadence for anomalies and errors, while educating HR staff and administrators on data quality standards and the importance of maintaining integrity. Identify key performance metrics such as data quality, distribution, bias, drift, and labeling accuracy and establish automated systems for real-time tracking and logging across all data sources. Monitor data for anomalies, shifts, or bias to assess how these changes impact AI performance and ensure the system remains aligned with HR objectives. Implement feedback loops and apply corrective actions based on insights (e.g., retraining models, adjusting data pipelines). | Top 3 Data Quality Practices for Successful AI Application Development, What should I know about Data Observability?, 6 Best Practices to Implement Data Observability Tools for Data and AI Initiatives
Measure effectiveness of data in HR AI use cases | For each HR AI use case, set measurable goals for what the AI solution should achieve. Assess data quality by evaluating AI HR use case output for completeness, accuracy, consistency, and relevance to the chosen outcome. Determine relevant KPIs for each HR AI use case to measure value and data quality/performance. Regularly monitor the AI solution’s outputs against the defined KPIs. Continuously collect feedback from HR stakeholders and end-users, analyze outcomes, and refine data inputs or AI models to improve effectiveness. | How to Evaluate AI Data Readiness, 3 Actions to Improve Your Data, Analytics and AI Governance
Design AI solutions as part of HR technology strategy | Define AI’s role and purpose as part of HR technology strategy (e.g., improve efficiency, increase decision quality, enhance experience, etc.). Assess AI’s fit with existing HR technology roadmap and determine where it complements, replaces or overlaps exiting systems and planned investments. Sequence opportunities based on expected impact, data readiness, implementation complexity, and organizational sensitivity. Define what success looks like in operational and employee experience terms so AI is linked to measurable and strategic outcomes. Define risks and potential failures associated with AI so accountability and ownership is clear. | How to Create an HR Technology Strategy and Roadmap 3 Failures that Break HR’s AI ROI and How to Avoid Them

## Slide 22: AI Data and Systems for HR Function: Detailed Activities (3 of 4)
Activity | Steps | Supporting resources
Define AI architecture, integration and controls | Determine where AI will sit in the technology stack (e.g., in a point solution, in a workflow layer, across multiple systems, etc.). Identify and map which systems the AI solution needs to access to function, which data it will consume, and what decisions/actions AI will influence. Set permissioning, access, and control boundaries to determine who can configure it and who can use it. Ensure the system design reflects privacy, legal, security, and bias requirements from the start. Specify where human oversight, escalation, exception handling and approvals are needed. | Prepare for the Future of AI Agents in HR Reference Architecture Brief: Infrastructure Platform Engineering
Create an AI runtime and execution environment | Define the operating environment for each AI use case, including models, tools, interfaces, workflows, and data environments for the AI solution to operate in. Set execution rules and define when the AI can act, recommend, escalate, and stand down. Create monitoring and observability mechanisms to track usage, output quality, failure patterns, user behavior and potential drift over time. Establish incident management process by defining how errors, hallucinations, potential breaches or harmful outputs will be reported and handled. Assign clear operational ownership over AI runtime health, issue resolution, tuning and ongoing support post go-live. | Tool: Craft a Code of Conduct for AI Agents to Govern Them Reference Architecture Brief: Best Practice Framework for Observability and Incident Response
Separate workflows from tools | Document system workflows and processes and distinguish business tasks from enabling tools. Redesign the workflow and intentionally place AI where it improves the workflow, judgment, speed or consistency. Ensure the workflow can still operate when the AI solution fails by designing fallbacks and alternative steps. Ensure HR retains ownership of workflow process logic, decision standards and accountability; avoid outsourcing workflow ownership to vendor solutions. | Elevate HR Processes with AI Agentic Workflows Tool: HR Process Redesign Methodology What Kind of Work Still Matters in the Age of AI?
Define AI's role at the system level | Clarify AI’s role in each use case (e.g., assisting, recommending, predicting, orchestrating, automating, etc.). Specify where AI can inform human judgement, where it triggers next steps, and where it cannot determine outcomes. Determine which tasks require human review, which can be machine-led, and which requires shared logic. Define human accountability over AI outputs, decisions, exceptions, and corrections in use cases. Test if the assigned AI role matches the organization’s overall AI readiness. | Leadership Agency: How CHROs Stay Ahead in the AI Era Tool: Craft a Code of Conduct for AI Agents to Govern Them
Configure AI with extensibility and platform controls | Shape how AI will behave with task guidance, response boundaries, tone, and decision/escalation logic. Set platform-level controls on model access, data handling, user permissions, and configuration rights. Define extensibility requirements and determine if the AI solution needs APIs, connectors, custom skills, or external data sources. | Toolkit: AI Controls for Governance of Models, Frameworks and Agents AI Governance Controls Must be Embedded into System Design

## Slide 23: AI Data and Systems for HR Function: Detailed Activities (4 of 4)
Activity | Steps | Supporting resources
Manage AI features in HR technology portfolio | Inventory AI capabilities across the HR technology stack and assess for overlaps, redundancy and fragmentation. Set ownership for ongoing feature management and define who reviews new vendor releases, approves activation, tracks performance, etc. Create a standard and treat AI configuration changes as managed system changes with approval, testing, documentation and rollback options. Test the configured AI in realistic scenarios to confirm that controls, outputs and exception handling all function as intended. Integrate AI feature decisions into broader HR technology portfolio governance and review it alongside architecture, contracts, budget, and workforce impact. | Top 3 Practices for Scaling GenAI Infrastructure Market Guide for API and MCP Testing Tools